## Slide 1: 2 years, 200 applications: A .NET Core Migration at Enterprise Scale
Lizzy Gallagher
Senior Software Development Engineer
Mastercard

## Slide 2: Our Goal
Migrate all applications in our platform to .NET Core

## Slide 3
Our Platform
160 web applications
90 console applications
300 internal NuGet packages

## Slide 4
Our Platform
Product #1
160 web applications
90 console applications
300 internal NuGet packages

## Slide 5
Our Platform
Product #2
160 web applications
90 console applications
300 internal NuGet packages
Product #1

## Slide 6
Our Platform
Product #2
160 web applications
90 console applications
300 internal NuGet packages
Product #1
Foundational Services

## Slide 7: Our Goal
Migrate all applications in our platform to .NET Core

## Slide 8: Our Goal
Migrate actively developed applications in our platform to .NET Core

## Slide 9: Who should do the migration?

## Slide 10: Who should do the migration?
 | Migration Expert | Application Expert
Top priority | .NET Core migration | Product features
Application knowledge | Shallow | Deep
Migration knowledge | Deep | Shallow

## Slide 11: Who should do the migration?
 | Migration Expert | Application Expert
Top priority | .NET Core migration | Product features
Application knowledge | Shallow | Deep
Migration knowledge | Deep | Shallow

## Slide 12: Both should play a role
Migration Expert will…
Lead research effort
Develop automated migrations for 95% of the changes
Provide support during migrations (e.g. office hours, on-call)
Application Expert will…
Schedule migration (around feature development)
Run the migration and do the remaining 5% changes manually
Test affected functionality
Raise concerns or suggest improvements

## Slide 13: Our Goal
Migrate actively developed applications in our platform to .NET Core

## Slide 14: Our Goal
Empower product teams to migrate all actively developed applications in our platform to .NET Core

## Slide 15: What strategy should we use?

## Slide 16: What strategy should we use?
 | All at once! | Incremental phases
Research | Need to understand whole migration before starting to migrate. | Only need to understand a phase just before starting it
Timing | Hard to find a month of time to do update | Easier to find a few days a few times a year for incremental updates
Stability | Everything changes (e.g. CI / CD, lots of APIs) | Changes and instability is chunked.

## Slide 17: What strategy should we use?
 | All at once! | Incremental phases
Research | Need to understand whole migration before starting to migrate. | Only need to understand a phase just before starting it
Timing | Hard to find a month of time to do update | Easier to find a few days a few times a year for incremental updates
Stability | Everything changes (e.g. CI / CD, lots of APIs) | Changes and instability is chunked.

## Slide 18: Our Goal
Empower product teams to migrate all actively developed applications in our platform to .NET Core

## Slide 19: Our Goal
Empower product teams to incrementally migrate all actively developed applications our platform to .NET Core

## Slide 20: What are the steps per-phase?
Manual Conversion
After research, migrate a solution by hand.
Do not merge, but keep track of all changes

## Slide 21: What are the steps per-phase?
Manual Conversion
Automate Conversion
After research, migrate a solution by hand.
Do not merge, but keep track of all changes
Create a LINQPad script to automate all the manual changes

## Slide 22: What are the steps per-phase?
Manual Conversion
Automate Conversion
“Dogfood” applications
After research, migrate a solution by hand.
Do not merge, but keep track of all changes
Create a LINQPad script to automate all the manual changes
Use script to migrate own applications, update script with manual changes
Deploy applications and closely monitor errors / uptime

## Slide 23: What are the steps per-phase?
Manual Conversion
Automate Conversion
“Dogfood” applications
“Fast track” applications
After research, migrate a solution by hand.
Do not merge, but keep track of all changes
Create a LINQPad script to automate all the manual changes
Use script to migrate own applications, update script with manual changes
Deploy applications and closely monitor errors / uptime
Use script to migrate volunteer applications

## Slide 24: What are the steps per-phase?
Manual Conversion
Automate Conversion
“Dogfood” applications
“Fast track” applications
Wide release!
After research, migrate a solution by hand.
Do not merge, but keep track of all changes
Create a LINQPad script to automate all the manual changes
Use script to migrate own applications, update script with manual changes
Deploy applications and closely monitor errors / uptime
Use script to migrate volunteer applications
Release documentation and script to everyone
Track adoption and follow up with lagging teams

## Slide 25: What are the five phases?
Phase 1
Update 3rd-party NuGet dependencies to .NET Standard-compatible versions
Phase 2
Update to “Sdk” project file format
Phase 3
Update from ASP.NET to ASP.NET Core

## Slide 26: What are the five phases?
Phase 4
Update internal NuGet packages to target .NET Standard 2.0
Phase 5
Target .NET Core 3.1

## Slide 27: Phase 1: 3rd Party NuGet packages
Major version updates to Autofac (IOC library) and NUnit (Unit testing library)
Incremental benefit?
  New features from the package versions(e.g. test parallelization).
Work required?
  Update internal NuGet packages, new application template
  Migration script to refactor around breaking changes
  Update CI test runner

## Slide 28: Phase 2: “Sdk” project file format
Update from “old” .csproj to “Sdk” format
Incremental benefit?
  Simpler package management model
  Way fewer .csproj merge conflicts!
Work required?
  Research correct setup for legacy ASP.NET applications
  Migration script

## Slide 29: Phase 3: ASP.NET Core
Update web applications from ASP.NET to ASP.NET Core.
Incremental benefit?
  ASP.NET Core feature set
  No more ConfigureAwait(false)!
Work required?
  Migration script for common code patterns
  Release ASP.NET Core-specific versions of WebApi / Mvc specific internal libraries
  Add deployment support

## Slide 30: Phase 4: .NET Standard
Update internal NuGet packages to target .NET Standard 2.0.
Incremental benefit?
  Used multi-targeting to drop legacy APIs while keeping 100% compatibility for .NET Framework consumers
  Unlocks the .NET CLI
Work required?
  Convert 100% of (non-deprecated) internal libraries!
  Migration script to update dependencies

## Slide 31: Phase 5: .NET Core!
Update all applications to target .NET Core 3.1.
Incremental benefit?
  .NET Core performance!
  .NET Core features!
  A feeling of accomplishment.
Work required?
  Minor deployment changes

## Slide 32: What didn’t go well?
Incremental updates are intrinsically less motivating
  If the phases are too small, product teams feel like they are being told to “eat your vegetables”
  If you release too many phases in quick succession, product teams can feel churn fatigue
  Ended up “bundling” extra features into the phases to make the updates more interesting

## Slide 33: What didn’t go well?
“One size fits all” automation does not actually fit all applications
  Applications that had innovated beyond the template were disproportionately left with more manual work
  Also affected, older applications using patterns that had fallen out of favor internally, e.g. complex ModelBinders
  Our “fast track” process helped mitigate this pain point during later phases

## Slide 34: What didn’t go well?
The incremental approach is not well-supported by tooling
  IDEs, deployment, and the dotnet CLI all had gaps in support
  e.g. the Visual Studio “Debug” menu does not work for an ASP.NET Application using the Sdk project file format
  This meant we spent more time than planned on implementing workarounds to maintain the developer experience

## Slide 35: Summary
We made two big choices upfront:
  Split effort between migration and application experts
  Separate the migration into 5 sequential phases
These two choices (and our excellent product teams) made this migration possible for our 200+ applications in 2+ years.

## Slide 36: Thanks for joining!
Elizabeth.Gallagher@mastercard.com
@LizzyIsNotBusy